MICROSERVICES MIGRATION

Technical Design Document

Document Version: v1.0

Status: Draft for Review

Prepared By: Enterprise Architecture Team

Date: July 2025

Classification: Internal – Confidential

# Table of Contents

1.  Executive Summary

2.  Project Overview

2.1  Current State Architecture

2.2  Target Microservices Architecture

2.3  Business Drivers and Rationale

2.4  Success Criteria

3.  Architecture Design

3.1  Current Monolithic Architecture Components

3.2  Target Microservices Architecture Components

3.3  Integration Patterns and API Gateway Design

3.4  Data Architecture and Database Strategy

4.  Migration Strategy

5.  Timeline

6.  Risk Matrix

7.  Technical Considerations

8.  Resource Requirements

9.  Success Metrics and KPIs

10.  Appendices

# 1. Executive Summary

This Technical Design Document (TDD) presents the comprehensive plan for migrating the existing monolithic enterprise application to a cloud-native microservices architecture. The migration initiative is driven by the need to address scalability constraints, accelerate the pace of feature delivery, and align the technology landscape with modern engineering best practices.

The current monolithic system—comprising tightly coupled modules for order management, inventory, customer management, billing, and reporting—has reached a critical inflection point. Deployment cycles that once took days now take weeks, a single component failure threatens the entire platform, and the cost of horizontal scaling is prohibitively high. The migration to microservices will decompose these modules into independently deployable, loosely coupled services, each owning its data and exposing well-defined APIs.

Expected outcomes of this initiative include a 60% reduction in mean time to deploy (MTD), a 40% improvement in system availability (targeting 99.95% SLA), independent scalability of individual services, and a marked improvement in developer productivity through smaller, autonomous team ownership. The migration will be executed in six structured phases over an estimated 18-month programme, employing the Strangler Fig pattern to minimise business disruption and provide clear rollback checkpoints at each phase.

# 2. Project Overview

## 2.1  Current State Architecture

The existing platform is a Java EE monolithic application deployed on a cluster of on-premises WebLogic application servers backed by a single Oracle 19c relational database. All business domains share a common codebase, a unified deployment pipeline, and a centralised data store. Key characteristics of the current state include:

Single deployable WAR/EAR artifact containing all business logic across six functional domains.

Shared Oracle 19c database with 380+ tables and tightly coupled schema relationships.

Monolithic session management via centralised HTTP sessions on WebLogic clusters.

Batch processing handled by Quartz Scheduler embedded within the application.

External integrations managed through point-to-point SOAP/REST calls with no intermediary.

No container orchestration; deployments are manual and error-prone, averaging 4–6 hours.

Limited horizontal scalability — the entire application must scale even if only one domain is under load.

## 2.2  Target Microservices Architecture

The target architecture decomposes the monolith into twelve domain-aligned microservices deployed on a Kubernetes (EKS) cluster on AWS. Each service is independently deployable, owns its data store, communicates via well-defined REST/gRPC APIs or asynchronous events (Apache Kafka), and is managed through a fully automated CI/CD pipeline. Key architectural attributes include:

Twelve bounded-context services aligned to Domain-Driven Design (DDD) principles.

API Gateway (AWS API Gateway + Kong) providing unified ingress, authentication, and rate limiting.

Event-driven architecture using Apache Kafka for asynchronous inter-service communication.

Per-service databases following the Database-per-Service pattern (PostgreSQL, MongoDB, Redis).

Service mesh (Istio) for mTLS, traffic management, and observability.

Centralised observability stack: Prometheus, Grafana, Jaeger (distributed tracing), and ELK.

GitOps-based deployment using ArgoCD with automated canary releases and rollback.

## 2.3  Business Drivers and Rationale

Scalability: Inability to scale individual modules leads to over-provisioning and high infrastructure costs.

Deployment Velocity: Release cycles average 3–4 weeks; competitors release multiple times per day.

Reliability: A single defect in any module can cause a full platform outage (current MTTR: ~6 hours).

Talent Acquisition: Engineers increasingly prefer cloud-native, container-based technology stacks.

Regulatory Compliance: Isolated services simplify PCI-DSS and GDPR data boundary enforcement.

Cost Optimisation: Fine-grained autoscaling reduces compute costs estimated at 35% annually.

## 2.4  Success Criteria

All twelve microservices deployed to production with zero data loss.

System availability ≥ 99.95% measured over a 30-day post-migration window.

Mean time to deploy (MTD) reduced from ~4 hours to < 15 minutes.

Independent scalability demonstrated under peak load testing for each service.

All existing integration touchpoints validated with downstream systems.

Full rollback capability maintained at each migration phase gate.

Developer onboarding time reduced by 50% through service isolation.

# 3. Architecture Design

## 3.1  Current Monolithic Architecture Components

The table below catalogues all identifiable components within the current monolithic system, their technology stack, dependencies, and functional description.

| Component Name | Type | Technology Stack | Dependencies | Description |
| --- | --- | --- | --- | --- |
| Order Management Module | Business Logic | Java EE 8, EJB 3.2 | Customer Mgmt, Inventory, Billing DB Schema | Manages end-to-end order lifecycle: creation, validation, fulfilment, and status tracking. Handles ~50K orders/day. |
| Inventory Management Module | Business Logic | Java EE 8, EJB 3.2 | Order Mgmt, Supplier Module, Oracle DB | Controls stock levels, warehouse allocations, reservation logic, and replenishment triggers. |
| Customer Management Module | Business Logic | Java EE 8, JSF 2.3 | Auth Module, Billing, Oracle DB | Manages customer profiles, preferences, address book, and loyalty programme. |
| Billing & Payments Module | Business Logic | Java EE 8, EJB 3.2 | Order Mgmt, Customer Mgmt, Payment Gateway API | Processes invoices, payment collection, refunds, and integrates with third-party payment gateways. |
| Reporting & Analytics Module | Business Logic | Java EE 8, JasperReports 6 | All Modules, Oracle DB (read replica) | Generates operational and management reports; executes complex SQL queries on read replica. |
| Notification Module | Business Logic | Java EE 8, JavaMail | Customer Mgmt, Order Mgmt, SMTP Server | Sends email, SMS, and push notifications triggered by domain events. |
| Authentication Module | Cross-Cutting | JAAS, LDAP/AD | Oracle DB (user tables), LDAP Server | Manages user identity, session tokens, role-based access control (RBAC). |
| Batch Processing Engine | Infrastructure | Quartz Scheduler 2.3 | All Modules, Oracle DB | Executes nightly batch jobs: inventory reconciliation, billing cycles, report generation. |
| Oracle 19c Database | Data Store | Oracle 19c RAC | All Modules | Single shared RDBMS with 380+ tables. Acts as system of record for all business domains. |
| WebLogic Cluster | Application Server | WebLogic 14c | Oracle DB, LDAP, SMTP, Payment Gateway | Hosts the monolithic WAR. Clustered for HA; no auto-scaling capability. |
| Apache HTTP Server | Web / Load Balancer | Apache HTTPD 2.4, mod_jk | WebLogic Cluster | Reverse proxy and load balancer distributing traffic across WebLogic managed servers. |
| Legacy ESB | Integration | Oracle Service Bus 12c | SOAP endpoints of all modules, External Partners | Mediates SOAP-based integrations with ERP, 3PL, and payment gateway. Introduces bottleneck. |
| File Transfer Service | Integration | SFTP, Shell Scripts | Batch Processing Engine, Oracle DB | Handles file-based B2B data exchange with suppliers and logistics partners. |
| Supplier Portal Module | Business Logic | Java EE 8, JSF 2.3 | Inventory Mgmt, Oracle DB, LDAP | Web portal for suppliers to manage catalogue, shipments, and invoices. |

Table 3.1 – Current Monolithic Architecture Component Inventory

## 3.2  Target Microservices Architecture Components

The following table defines the twelve target microservices, their technology stacks, inter-service dependencies, and responsibilities within the new architecture.

| Service Name | Type | Technology Stack | Dependencies | Description |
| --- | --- | --- | --- | --- |
| Order Service | Domain Service | Node.js 20, TypeScript, PostgreSQL 15 | Inventory Svc, Customer Svc, Kafka | Core order lifecycle management. Publishes OrderCreated, OrderUpdated events to Kafka topics. |
| Inventory Service | Domain Service | Python 3.12, FastAPI, PostgreSQL 15 | Order Svc (Kafka), Supplier Svc, Redis | Real-time stock management, reservation handling, and reorder triggers. Redis for stock cache. |
| Customer Service | Domain Service | Java 21 (Spring Boot 3), PostgreSQL 15 | Auth Service, Notification Svc, Kafka | Customer profile, loyalty, and preference management. Publishes CustomerUpdated events. |
| Billing Service | Domain Service | Java 21 (Spring Boot 3), PostgreSQL 15 | Order Svc, Customer Svc, Payment Gateway | Invoice generation, payment processing, refunds. Consumes OrderFulfilled Kafka events. |
| Notification Service | Domain Service | Go 1.22, MongoDB 7 | Kafka (all topics), SNS, SES, FCM | Stateless event-driven notification dispatcher. Consumes domain events; routes to email/SMS/push. |
| Auth Service | Platform Service | Java 21 (Spring Security), Redis, PostgreSQL | LDAP/AD (migration phase), Vault | OAuth 2.0 / OpenID Connect provider. Issues JWT tokens. Redis session cache. Integrates with Vault. |
| Supplier Service | Domain Service | Python 3.12, FastAPI, PostgreSQL 15 | Inventory Svc (Kafka), File Storage (S3) | Supplier catalogue, shipment tracking, and invoice submission. S3 for document storage. |
| Reporting Service | Domain Service | Python 3.12, Apache Spark, MongoDB 7 | Read replicas of all domain DBs, S3 | Async report generation. Spark jobs consume from PostgreSQL read replicas; results to S3/MongoDB. |
| Search Service | Platform Service | Java 21, Elasticsearch 8 | Order Svc, Inventory Svc, Customer Svc | Full-text and faceted search across orders, products, and customers. Fed by Kafka change events. |
| API Gateway | Infrastructure | AWS API Gateway, Kong 3.6 | All Domain Services, Auth Service | Single ingress point. Handles routing, rate limiting, JWT validation, and API versioning. |
| Event Bus | Infrastructure | Apache Kafka 3.7, Confluent Schema Registry | All Domain Services | Backbone for asynchronous inter-service messaging. Schema Registry enforces Avro contract. |
| Service Mesh | Infrastructure | Istio 1.21, Envoy Proxy | Kubernetes (EKS 1.30), All Services | mTLS, traffic shaping, circuit breaking, and distributed tracing (integrates with Jaeger). |
| Config & Secret Service | Platform Service | HashiCorp Vault 1.16, AWS SSM | All Services | Centralised secrets management, dynamic credentials, and configuration store. |
| Observability Stack | Infrastructure | Prometheus, Grafana, Jaeger, ELK 8 | All Services, Kubernetes | Metrics collection (Prometheus), dashboards (Grafana), distributed tracing (Jaeger), log aggregation (ELK). |

Table 3.2 – Target Microservices Architecture Component Inventory

## 3.3  Integration Patterns and API Gateway Design

The table below documents the integration patterns adopted for inter-service communication and the API Gateway configuration applied across service domains.

| Pattern / Component | Type | Technology | Services Involved | Use Case & Configuration Details |
| --- | --- | --- | --- | --- |
| Synchronous REST API | Communication Pattern | HTTP/1.1, JSON, OpenAPI 3.1 | All domain services | Request-response for real-time queries. Enforced via Kong plugin with schema validation and OpenAPI spec publishing. |
| Synchronous gRPC | Communication Pattern | HTTP/2, Protocol Buffers 3 | Auth Svc ↔ All, Inventory ↔ Order | Low-latency internal service calls. Protobuf contracts stored in shared registry. Used where sub-10ms latency required. |
| Asynchronous Event Streaming | Communication Pattern | Apache Kafka 3.7, Avro | All domain services via Event Bus | Domain event publication and subscription. Topics: orders, inventory, billing, customers, notifications. Retention: 7 days. |
| API Gateway – Routing | Gateway Feature | AWS API Gateway + Kong | External clients → All services | URL-based routing rules map /api/v1/orders/* → Order Service. Supports path rewriting and versioning. |
| API Gateway – Auth | Gateway Feature | Kong JWT Plugin, Auth Service | All inbound API requests | JWT validation at gateway edge before forwarding to upstream. Token introspection for third-party OAuth flows. |
| API Gateway – Rate Limiting | Gateway Feature | Kong Rate Limiting Advanced Plugin | All public API consumers | Tiered rate limits: Free tier 100 req/min; Premium 1000 req/min; Internal 10,000 req/min. |
| API Gateway – Circuit Breaker | Gateway Feature | Kong, Istio (Envoy) | All upstream services | Configures 50% error threshold circuit breaker with 30-second open window before half-open retry. |
| Service Mesh mTLS | Security Pattern | Istio, Envoy, SPIFFE/SPIRE | All pod-to-pod communication | Mutual TLS enforced for all east-west traffic within the cluster. Certificates rotated every 24 hours automatically. |
| Saga Pattern (Choreography) | Communication Pattern | Apache Kafka, Compensating Txns | Order, Billing, Inventory services | Distributed transaction management for order fulfilment flow. Each service publishes success/failure events to trigger next step or compensating action. |
| CQRS | Data Pattern | Kafka, Elasticsearch, MongoDB | Order Svc, Search Svc, Reporting Svc | Command (write) operations go to PostgreSQL; queries served from Elasticsearch or MongoDB read models updated via Kafka. |
| Webhook Callbacks | Integration Pattern | HTTPS, HMAC Signature Verification | Billing Svc ↔ Payment Gateway | Payment gateway notifies Billing Service of transaction outcomes via signed webhook. Idempotency key enforced. |
| BFF (Backend for Frontend) | Architecture Pattern | Node.js, GraphQL | Web UI, Mobile App → Domain Services | Separate BFF aggregates for web (GraphQL) and mobile (REST) clients. Reduces over-fetching and simplifies frontend logic. |

Table 3.3 – Integration Patterns and API Gateway Design

## 3.4  Data Architecture and Database Strategy

The Database-per-Service pattern is the cornerstone of the data architecture. Each service owns its schema and no other service may query it directly. Cross-service data needs are satisfied via APIs or event-driven read models.

| Service | Database Technology | Database Type | Data Isolation Strategy | Migration Approach | Estimated Data Volume |
| --- | --- | --- | --- | --- | --- |
| Order Service | PostgreSQL 15 (AWS RDS) | Relational | Dedicated RDS instance; no shared schema | Extract from Oracle using AWS DMS; dual-write during transition | ~120 GB; 50K orders/day |
| Inventory Service | PostgreSQL 15 (AWS RDS) + Redis 7 | Relational + Cache | Dedicated RDS + ElastiCache cluster | Oracle DMS extract; Redis seeded from PostgreSQL warm-up job | ~45 GB; Redis TTL 300s |
| Customer Service | PostgreSQL 15 (AWS RDS) | Relational | Dedicated RDS Multi-AZ; row-level encryption | Oracle DMS extract; PII fields re-encrypted with AWS KMS | ~30 GB; 2M customer records |
| Billing Service | PostgreSQL 15 (AWS RDS) | Relational | Dedicated RDS; financial audit trail preserved | Oracle DMS extract; reconciliation job validates totals | ~200 GB; 7-year retention |
| Notification Service | MongoDB 7 (DocumentDB) | Document | DocumentDB cluster; TTL index on log docs | No migration; fresh start with event replay from Kafka | ~10 GB growing; TTL 90 days |
| Auth Service | PostgreSQL 15 + Redis 7 | Relational + Cache | Dedicated RDS; Redis for token store | LDAP → PostgreSQL user sync; password re-hash at first login | ~5 GB; 500K user records |
| Supplier Service | PostgreSQL 15 (AWS RDS) | Relational | Dedicated RDS; S3 for binary documents | Oracle DMS extract; S3 migration of file attachments | ~25 GB DB; ~500 GB S3 |
| Reporting Service | MongoDB 7 (DocumentDB) + S3 | Document + Object | Read-only replicas + S3 data lake | Rebuild from Kafka event replay + historical Oracle snapshot | ~1 TB S3; 50 GB MongoDB |
| Search Service | Elasticsearch 8 (AWS OpenSearch) | Search Index | Dedicated domain; index-per-entity model | Bulk index from source services post-migration; Kafka ongoing | ~80 GB index |
| Shared Event Store | Apache Kafka 3.7 (MSK) | Event Log | Topic-per-domain; RBAC on consumer groups | New deployment; historical events backfilled from Oracle CDC | 7-day retention; ~2 TB peak |

Table 3.4 – Data Architecture and Database Strategy per Service

# 4. Migration Strategy

## 4.1  Decomposition Approach – Strangler Fig Pattern

The migration adopts the Strangler Fig Pattern — progressively routing traffic away from the monolith to newly deployed microservices while keeping the legacy system operational as a fallback. A feature flag and traffic-splitting layer (via the API Gateway) controls the percentage of traffic directed to each new service, enabling gradual cut-over with immediate rollback capability.

## 4.2  Service Identification and Bounded Contexts

Services are identified using Domain-Driven Design (DDD) Event Storming workshops. Each bounded context maps to exactly one microservice. The following principles guide service boundary definitions:

Single Responsibility: Each service encapsulates one and only one business capability.

High Cohesion / Loose Coupling: Services share no database tables and communicate only via API or events.

Team Alignment (Conway's Law): Service boundaries align to autonomous squad ownership (2-pizza rule).

Independent Deployability: Any service can be deployed, scaled, or rolled back without affecting others.

Data Ownership: Each service is the sole writer of its own data store.

## 4.3  Phased Decomposition Sequence

Services are migrated in the following priority order based on blast radius, data coupling complexity, and business value:

| Phase | Services Migrated | Rationale |
| --- | --- | --- |
| Phase 1 – Foundation | Auth Service, API Gateway, Event Bus, Service Mesh, Observability Stack | Low blast radius; enables secure scaffolding for subsequent services. |
| Phase 2 – Customer Core | Customer Service, Notification Service | Relatively low data coupling; high business value for personalisation roadmap. |
| Phase 3 – Commerce Core | Order Service, Inventory Service | Highest transaction volume; requires Saga pattern implementation for consistency. |
| Phase 4 – Financial | Billing Service, Supplier Service | Complex financial data migration; requires dual-write reconciliation period. |
| Phase 5 – Intelligence | Reporting Service, Search Service | Read-only workloads; can be rebuilt from event replay with no data loss risk. |
| Phase 6 – Decommission | Legacy Monolith, Oracle ESB, WebLogic Cluster | Final traffic cut-over, decommission of legacy systems, and Oracle DB archival. |

Table 4.1 – Phased Service Decomposition Sequence

## 4.4  Data Migration Approach

Schema Extraction: Oracle schema analysed with AWS Schema Conversion Tool (SCT) to identify target schemas per service.

Data Replication: AWS Database Migration Service (DMS) used for initial full-load and ongoing CDC replication.

Dual-Write Period: New services write to both old Oracle tables and new PostgreSQL schemas during transition to ensure consistency.

Data Validation: Automated reconciliation jobs compare row counts, checksums, and financial totals between source and target.

Cut-Over: Traffic switched to new service once validation passes. Old Oracle tables become read-only for 30-day audit window.

PII Handling: All Personally Identifiable Information re-encrypted using AWS KMS customer-managed keys during migration.

Rollback: DMS reverse replication configured to allow rollback within 72 hours of cut-over at each phase.

## 4.5  Testing Strategy

| Test Type | Scope | Tooling | Approach & Criteria |
| --- | --- | --- | --- |
| Unit Testing | Each service | JUnit 5, pytest, Jest | >80% code coverage; automated in CI pipeline on every commit. |
| Contract Testing | API boundaries | Pact (Consumer-Driven Contracts) | Consumer-driven contract tests published to Pact Broker; verified on provider side before merge. |
| Integration Testing | Service pairs | Testcontainers, Docker Compose | Spin up dependent services as containers; test real API and Kafka interactions. |
| End-to-End Testing | Full flow | Cypress, Selenium, k6 | Critical user journeys automated in staging environment mirroring production topology. |
| Performance Testing | All services | k6, Gatling, AWS Load Testing | Baseline benchmarks established; 2x peak load tests before each phase cut-over. |
| Chaos Engineering | Production readiness | Chaos Monkey, Litmus Chaos (K8s) | Inject failure scenarios (pod kill, network partition, DB failover) to validate resilience. |
| Security Testing | All services | OWASP ZAP, Trivy, Snyk | DAST, container image scanning, dependency vulnerability scanning in CI/CD pipeline. |
| Data Migration Testing | Data layer | Custom reconciliation scripts, DMS | Row count, checksum, and business-rule validation after each DMS migration batch. |
| UAT | Business acceptance | Manual + Exploratory Testing | Business stakeholders validate key workflows in staging; sign-off required before production cut-over. |

Table 4.2 – Testing Strategy and Tooling

# 5. Project Timeline

The project is structured into six phases spanning 18 months. Each phase concludes with a phase gate review requiring formal sign-off before the next phase commences. Dates are indicative and subject to phase gate approval.

| Phase | Key Activities | Duration | Start Date | End Date | Dependencies |
| --- | --- | --- | --- | --- | --- |
| Phase 0 Initiation & Planning | • Stakeholder alignment & sponsor sign-off • Detailed scope definition & backlog grooming • Team formation & onboarding • Vendor selection (AWS, Kong, Confluent) • Architecture review board approval • Risk register establishment | 6 Weeks | Aug 4, 2025 | Sep 12, 2025 | Executive sponsorship Budget approval |
| Phase 1 Foundation & Platform Setup | • AWS EKS cluster provisioning (multi-AZ) • Istio service mesh deployment • Kafka (MSK) cluster setup & topic design • API Gateway (Kong) initial configuration • Observability stack (Prometheus/Grafana/Jaeger/ELK) • HashiCorp Vault deployment • CI/CD pipeline scaffolding (GitLab CI + ArgoCD) • Base container images & golden path templates | 10 Weeks | Sep 15, 2025 | Nov 21, 2025 | Phase 0 complete AWS accounts provisioned Network topology approved |
| Phase 2 Auth, Customer & Notification Services | • Auth Service build & OAuth2/OIDC implementation • LDAP/AD migration to PostgreSQL user store • Customer Service build & Oracle DMS extraction • Notification Service build (Kafka consumer) • API Gateway JWT integration • Consumer-driven contract tests established • Staging environment validation & UAT • Phased traffic cut-over (10% → 50% → 100%) | 12 Weeks | Nov 24, 2025 | Feb 13, 2026 | Phase 1 complete DMS access to Oracle Customer data PII review |
| Phase 3 Order & Inventory Services | • Order Service build (Node.js/TypeScript) • Inventory Service build (Python/FastAPI) • Saga choreography pattern implementation • Redis cache layer setup for Inventory • Kafka topic creation: orders, inventory • Performance testing (2x peak load) • Dual-write period: Oracle + PostgreSQL • Data reconciliation & validation • Staging UAT & phase gate review • Canary deployment: 5% → 25% → 100% | 14 Weeks | Feb 16, 2026 | May 22, 2026 | Phase 2 complete Saga pattern approved by architects Load test environment ready |
| Phase 4 Billing & Supplier Services | • Billing Service build (Spring Boot / Java 21) • Payment gateway webhook integration • Supplier Service build & S3 document migration • Financial data migration with dual-write • Audit trail validation & reconciliation • PCI-DSS compliance review • Supplier portal re-implementation • E2E testing of payment flows • Phase gate: financial sign-off required | 14 Weeks | May 25, 2026 | Aug 28, 2026 | Phase 3 complete PCI-DSS assessment scheduled Finance team sign-off process |
| Phase 5 Reporting & Search Services | • Reporting Service build (Python/Spark) • Historical data backfill from Oracle snapshot • Kafka event replay for read model build • Search Service (Elasticsearch/OpenSearch) build • Bulk indexing from source services • Report parity validation with legacy • Performance optimisation of Spark jobs • Business stakeholder report UAT | 10 Weeks | Aug 31, 2026 | Nov 6, 2026 | Phases 3 & 4 complete Historical Oracle snapshot exported S3 data lake provisioned |
| Phase 6 Cut-Over & Decommission | • Final 100% traffic cut-over to all microservices • Oracle DB set to read-only (30-day audit window) • WebLogic cluster graceful shutdown • Oracle ESB decommission • Legacy infrastructure cost reclamation • Post-migration monitoring (30-day hyper-care) • Final architecture documentation update • Lessons learned review • Oracle archive to S3 Glacier | 8 Weeks | Nov 9, 2026 | Jan 1, 2027 | All phases complete All services at 100% traffic Sign-off from all business units |

Table 5.1 – Detailed Project Timeline by Phase

# 6. Risk Matrix

The following risk matrix captures identified risks across technical, operational, and business categories. Risk Level is calculated as a combination of Probability and Impact: High × High = Critical; High × Medium or Medium × High = High; Medium × Medium = Medium; Low × any = Low or Medium.

| Risk ID | Risk Description | Category | Probability | Impact | Risk Level | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R-01 | Data loss or corruption during Oracle to PostgreSQL migration | Technical | High | High | Critical | Dual-write pattern; DMS CDC replication; automated reconciliation scripts; 72-hour rollback window; dry-run migration in staging x3 before production. | Data Architect |
| R-02 | Distributed transaction consistency failures across services (Saga failures) | Technical | Medium | High | High | Implement idempotent compensating transactions; comprehensive Saga integration test suite; chaos engineering tests for partial failure scenarios; dead-letter queue monitoring. | Lead Architect |
| R-03 | Performance degradation due to network latency in service-to-service calls | Technical | Medium | Medium | Medium | Adopt gRPC for latency-sensitive paths; implement Redis caching; set P99 latency SLOs per service; continuous performance testing in CI pipeline. | Platform Engineer |
| R-04 | Security vulnerabilities introduced through expanded attack surface | Technical | Medium | High | High | Zero-trust network policy via Istio mTLS; automated SAST/DAST in CI/CD; container image scanning (Trivy); quarterly penetration testing; secrets managed via Vault. | Security Architect |
| R-05 | Kubernetes cluster instability or misconfiguration causing outages | Technical | Low | High | Medium | Infrastructure-as-Code (Terraform) for all cluster config; multi-AZ node groups; PodDisruptionBudgets; automated runbook for node failure recovery; pre-production rehearsals. | DevOps Lead |
| R-06 | Kafka consumer lag causing delayed order processing and SLA breaches | Technical | Medium | High | High | Consumer group lag alerting at 10K message threshold; auto-scaling consumer pods via KEDA; dedicated Kafka partitions for high-priority order topics. | Platform Engineer |
| R-07 | Key personnel departure during migration programme | Operational | Medium | High | High | Cross-training all squad members; comprehensive runbooks and architecture decision records (ADRs); contractor contingency budget approved; no single point of expertise. | Programme Manager |
| R-08 | Scope creep leading to timeline slippage | Operational | High | Medium | High | Strict change control board process; phase gate reviews with formal scope confirmation; MoSCoW prioritisation applied to all backlog items; monthly steering committee oversight. | Programme Manager |
| R-09 | Third-party vendor delays (AWS, Kong, Confluent licensing) | Operational | Low | Medium | Low | Vendor contracts finalised in Phase 0; multi-vendor contingency (e.g., self-hosted Kafka as fallback for MSK); vendor SLA review monthly. | Programme Manager |
| R-10 | Inadequate monitoring leading to undetected production issues post cut-over | Operational | Medium | High | High | 30-day hyper-care period with 24/7 on-call rotation; pre-defined runbooks for all alert types; SLO/SLA dashboards visible to all stakeholders; automated anomaly detection (Grafana). | SRE Lead |
| R-11 | Business disruption during traffic cut-over | Business | Medium | High | High | Canary deployments (5%→25%→100%); feature flags for instant rollback; cut-overs scheduled during lowest-traffic windows (Sunday 02:00–04:00); business stakeholder sign-off mandatory. | Programme Manager |
| R-12 | Regulatory non-compliance (GDPR, PCI-DSS) during data migration | Business | Low | High | Medium | Data Protection Officer engaged from Phase 0; GDPR data mapping completed before migration; PCI-DSS QSA assessment in Phase 4; all PII encrypted in-transit and at-rest via AWS KMS. | Compliance Officer |
| R-13 | Stakeholder resistance and adoption challenges | Business | Medium | Medium | Medium | Executive sponsor communications plan; monthly all-hands progress updates; developer experience workshops; clear articulation of benefits per team; early wins communicated broadly. | Programme Manager |
| R-14 | Legacy Oracle ESB decommission dependency blocking migration timeline | Technical | Medium | Medium | Medium | Map all ESB integration flows in Phase 0; prioritise ESB route replacements in Phase 1 platform build; maintain ESB in parallel until all consumers migrated and validated. | Integration Architect |
| R-15 | Cost overrun due to cloud infrastructure underestimation | Business | Medium | Medium | Medium | FinOps review monthly with AWS Cost Explorer; reserved instances for baseline workloads; auto-scaling policies tuned to prevent idle over-provisioning; budget alerts at 80% threshold. | Cloud FinOps Lead |

Table 6.1 – Comprehensive Risk Assessment Matrix

# 7. Technical Considerations

## 7.1  Service Communication Patterns

The architecture employs a hybrid communication model:

Synchronous (REST/gRPC): Used for real-time, request-response interactions where the caller requires an immediate result (e.g., Auth token validation, stock availability checks).  gRPC is preferred for internal high-frequency calls due to its binary serialisation efficiency (~7x smaller payload vs JSON) and native streaming support.

Asynchronous (Kafka Events): Used for domain events where eventual consistency is acceptable (e.g., order placed, payment completed). This decouples producers from consumers, improving resilience. All events carry a correlation ID for end-to-end tracing.

Service Mesh (Istio/Envoy): All inter-service HTTP traffic is transparently proxied through Envoy sidecars, providing automatic retry, circuit breaking (Hystrix-style), timeout enforcement, and traffic mirroring without application code changes.

Backpressure and Bulkhead: Thread pool isolation (Bulkhead pattern) and backpressure-aware Kafka consumers prevent cascade failures when downstream services are slow or unavailable.

## 7.2  Security and Authentication

OAuth 2.0 / OpenID Connect: Auth Service acts as the central identity provider (IdP). All client applications obtain JWT access tokens with 15-minute expiry. Refresh token rotation enforced.

Zero-Trust Networking: No implicit trust between services. mTLS enforced for all east-west traffic via Istio. Network policies (Kubernetes NetworkPolicy + Calico) restrict pod-to-pod communication to declared dependencies only.

Secrets Management: All credentials, API keys, and certificates managed by HashiCorp Vault. Dynamic secrets generated per-service with short TTLs. No secrets in environment variables or container images.

Container Security: All images built from hardened base images (distroless). Trivy scans in CI pipeline; critical/high CVEs block merge. Runtime security via Falco for anomaly detection.

API Security: OWASP Top 10 mitigations applied at API Gateway layer. Input validation via OpenAPI schema enforcement. DDoS protection via AWS Shield Standard + WAF rules.

Data Encryption: AES-256 encryption at rest for all databases (AWS RDS encryption). TLS 1.3 enforced for all data in transit. PII fields encrypted at application layer using AWS KMS CMKs.

## 7.3  Monitoring and Observability

The observability strategy is built on the three pillars: Metrics, Logs, and Traces.

Metrics: Prometheus scrapes metrics from all services via sidecar-injected metrics endpoints. Custom business metrics (orders/minute, payment success rate) alongside infrastructure metrics. Grafana dashboards per service and executive-level SLO dashboard.

Logs: All services emit structured JSON logs to stdout. Fluentd daemonsets collect and forward to Elasticsearch (via Logstash). Kibana for ad-hoc querying. Log retention: 30 days hot, 1 year cold (S3).

Distributed Tracing: OpenTelemetry SDK integrated into all services. Traces exported to Jaeger. 100% sampling in staging; 5% head-based + 100% error-based tail sampling in production. Trace IDs propagated via W3C TraceContext headers.

Alerting: Alertmanager routes alerts to PagerDuty (P1/P2) and Slack (P3/P4). SLO burn-rate alerting with 1-hour and 6-hour burn-rate windows to catch both fast and slow burns.

Synthetic Monitoring: Datadog Synthetics runs critical user journey checks every 60 seconds from multiple AWS regions. Alerts on availability, latency, and correctness.

Service-Level Objectives: Each service defines SLOs for availability (99.9%–99.99%), P99 latency, and error rate. SLO adherence is gated in the deployment pipeline.

## 7.4  DevOps and CI/CD Pipeline

Source Control: GitLab mono-repo per service domain. Branch protection on main; all changes via merge request with minimum 2 approvals and passing CI pipeline.

CI Pipeline (GitLab CI): Stages: lint → unit test → build Docker image → SAST (Semgrep) → container scan (Trivy) → publish to ECR → contract test → integration test (Testcontainers). Average pipeline time: target < 8 minutes.

CD Pipeline (ArgoCD + GitOps): ArgoCD monitors Helm chart repositories. Staging auto-deploys on main merge. Production deployments require manual approval gate. Canary rollout strategy configured via Argo Rollouts.

Infrastructure as Code: All AWS infrastructure (EKS, RDS, MSK, ElastiCache) defined in Terraform. State stored in S3 with DynamoDB lock. Infra changes require peer review and plan output approval.

Environment Parity: Four environments: dev (per-feature ephemeral), staging (mirrors production topology), pre-prod (performance/chaos testing), production. Environment configs managed via Helm values and Vault secrets.

Rollback Strategy: Automated rollback triggered if canary error rate exceeds 1% or P99 latency exceeds SLO for 5 consecutive minutes. ArgoCD rolls back Helm release to previous revision within 2 minutes.

# 8. Resource Requirements

## 8.1  Team Structure and Roles

| Role | Count | Responsibility | Engagement Model | Phase |
| --- | --- | --- | --- | --- |
| Programme Manager | 1 | Overall programme delivery, stakeholder management, risk and budget oversight, steering committee reporting. | Full-time, FTE | All phases |
| Enterprise Architect | 1 | Architecture governance, ADR oversight, cross-cutting concern design, external vendor liaison. | Full-time, FTE | All phases |
| Lead Solution Architect | 1 | Detailed service design, integration pattern definition, technology selection, API design standards. | Full-time, FTE | Phases 0–5 |
| Data Architect | 1 | Data migration strategy, DMS configuration, schema design, data governance, encryption standards. | Full-time, FTE | All phases |
| Security Architect | 1 | Zero-trust design, Vault setup, penetration test coordination, PCI-DSS / GDPR compliance oversight. | Full-time, FTE | All phases |
| DevOps / Platform Engineers | 3 | EKS cluster management, CI/CD pipeline build, Terraform IaC, Istio service mesh, observability stack setup. | Full-time, FTE | Phases 1–6 |
| SRE Lead | 1 | SLO definition, alerting strategy, runbook authoring, hyper-care on-call coordination, chaos engineering. | Full-time, FTE | Phases 3–6 |
| Backend Engineers (Squads) | 12 | Microservice implementation (2 engineers per service × 6 squads). Test-driven development, API design. | Full-time, FTE | Phases 2–5 |
| Frontend Engineers | 2 | BFF (GraphQL/REST) implementation, Supplier Portal re-implementation, UI integration testing. | Full-time, FTE | Phases 3–5 |
| QA / Test Engineers | 3 | Test strategy execution, contract testing, E2E automation, performance test scripting, UAT coordination. | Full-time, FTE | Phases 1–6 |
| DBA / Migration Engineers | 2 | Oracle schema analysis, AWS DMS setup, dual-write validation, reconciliation scripting, archival procedures. | Full-time, FTE | Phases 1–6 |
| Business Analysts | 2 | Requirements refinement, Event Storming facilitation, UAT support, acceptance criteria definition. | Full-time, FTE | Phases 0–5 |
| Cloud FinOps Analyst | 1 | AWS cost monitoring, reserved instance planning, budget alerting, monthly cost reporting to steering committee. | Part-time, 50% | Phases 1–6 |
| Compliance Officer | 1 | GDPR data mapping, PCI-DSS QSA coordination, privacy impact assessments, regulatory sign-off at phase gates. | Part-time, 25% | All phases |

Table 8.1 – Team Structure and Resource Requirements

## 8.2  Infrastructure Requirements

| Resource | Specification | Purpose | Sizing | Estimated Monthly Cost |
| --- | --- | --- | --- | --- |
| AWS EKS Cluster (Production) | EKS 1.30, Multi-AZ (3 AZs) | Kubernetes orchestration for all microservices | 12× m6i.2xlarge nodes (autoscaled 12–30) | ~$8,500/month |
| AWS EKS Cluster (Staging) | EKS 1.30, Single-AZ | Pre-production testing and validation environment | 6× m6i.xlarge nodes (fixed) | ~$2,200/month |
| AWS RDS PostgreSQL (per service) | PostgreSQL 15, Multi-AZ, db.r6g.xlarge | 10 dedicated RDS instances across all domain services | Storage: 50 GB–500 GB per instance | ~$6,800/month |
| Amazon MSK (Kafka) | Kafka 3.7, 3 brokers, Multi-AZ | Event streaming backbone for all asynchronous communication | 3× kafka.m5.2xlarge brokers | ~$2,400/month |
| Amazon ElastiCache (Redis) | Redis 7, Cluster mode, r6g.large | Session cache (Auth), stock cache (Inventory) | 3-node clusters per use case | ~$1,200/month |
| Amazon OpenSearch | Elasticsearch 8 compatible, 3 nodes | Search Service index store | r6g.xlarge.search × 3, 500 GB EBS | ~$1,800/month |
| Amazon DocumentDB (MongoDB) | MongoDB 7 compatible, 3 nodes | Notification and Reporting document stores | db.r6g.large × 3 | ~$1,400/month |
| AWS API Gateway + Kong | REST + HTTP API Gateway + Kong EE | API management, rate limiting, auth enforcement | Kong on EKS (3 replicas), AWS APIGW | ~$1,100/month |
| Amazon S3 | Standard + Glacier storage classes | Document storage, Spark output, log archives, DB backups | Estimated 5 TB standard, 20 TB Glacier | ~$800/month |
| HashiCorp Vault (HCP) | HCP Vault Plus tier | Secrets management, dynamic credentials, PKI | HCP managed cluster | ~$900/month |
| GitLab Ultimate (SaaS) | GitLab.com Ultimate plan | Source control, CI/CD pipelines, container registry | 30 users | ~$1,800/month |
| Monitoring (Grafana Cloud) | Grafana Cloud Pro + on-prem Prometheus | Metrics, alerting, dashboards | 500K series, 30-day retention | ~$700/month |

Table 8.2 – Infrastructure Resource Requirements and Cost Estimates

## 8.3  Tools and Technologies Summary

| Category | Tools / Technologies | Purpose |
| --- | --- | --- |
| Container Orchestration | Kubernetes (EKS 1.30), Helm 3, Kustomize | Container scheduling, service deployment, configuration management |
| Service Mesh | Istio 1.21, Envoy Proxy, SPIFFE/SPIRE | mTLS, traffic management, circuit breaking, observability |
| API Gateway | AWS API Gateway, Kong 3.6 Enterprise | API routing, authentication, rate limiting, developer portal |
| Event Streaming | Apache Kafka 3.7 (MSK), Confluent Schema Registry | Asynchronous inter-service events, event sourcing, CDC |
| IaC / GitOps | Terraform 1.8, ArgoCD 2.11, Argo Rollouts | Infrastructure provisioning, GitOps deployments, canary releases |
| CI/CD | GitLab CI/CD, Docker, AWS ECR | Automated build, test, security scan, and publish pipelines |
| Observability | Prometheus, Grafana, Jaeger, OpenTelemetry, ELK Stack | Metrics, dashboards, distributed tracing, log aggregation |
| Security | HashiCorp Vault, Trivy, Falco, OWASP ZAP, Snyk | Secrets, container scanning, runtime security, DAST, SCA |
| Data Migration | AWS DMS, AWS SCT, Custom reconciliation scripts | Oracle-to-PostgreSQL migration, CDC replication, validation |
| Testing | JUnit 5, pytest, Jest, Pact, Testcontainers, k6, Cypress | Unit, contract, integration, performance, and E2E testing |
| Programming Languages | Java 21, Python 3.12, Node.js 20 (TypeScript), Go 1.22 | Service implementation languages per bounded context |
| Cloud Provider | AWS (EKS, RDS, MSK, S3, KMS, WAF, CloudFront, etc.) | Primary cloud hosting and managed services platform |

Table 8.3 – Tools and Technologies Overview

# 9. Success Metrics and KPIs

The following KPIs and success metrics will be tracked throughout and after the migration programme. Baseline values are measured from the current monolithic system over a 90-day period prior to Phase 1. Target values are to be achieved within 90 days of the final production cut-over.

| KPI Category | Metric | Baseline (Current) | Target (Post-Migration) | Measurement Method | Review Frequency |
| --- | --- | --- | --- | --- | --- |
| Deployment Velocity | Mean Time to Deploy (MTD) | 4.2 hours | < 15 minutes | CI/CD pipeline deployment logs (GitLab) | Weekly |
| Deployment Velocity | Deployment Frequency | 1× per 3–4 weeks | ≥ 10× per week | GitLab deployment events per environment | Weekly |
| Deployment Velocity | Change Failure Rate | 12% | < 5% | Rollback events / total deployments | Weekly |
| Reliability | System Availability (SLA) | 99.7% | ≥ 99.95% | Synthetic monitoring uptime (Datadog) | Daily |
| Reliability | Mean Time to Recovery (MTTR) | ~6 hours | < 30 minutes | Incident management platform (PagerDuty) | Per incident |
| Reliability | Mean Time Between Failures (MTBF) | ~2 weeks | > 8 weeks | Incident log analysis | Monthly |
| Performance | API P99 Latency (Order Service) | ~850ms | < 200ms | Jaeger traces + Prometheus histogram metrics | Real-time |
| Performance | Throughput (Orders/second) | ~18 req/s peak | ≥ 80 req/s (scalable) | Load test results + production Prometheus metrics | Per release |
| Performance | Database Query P99 Latency | ~450ms | < 50ms | RDS Performance Insights + Prometheus | Real-time |
| Scalability | Scale-to-zero capability | Not supported | 100% of services | Kubernetes HPA/KEDA configuration audit | Monthly |
| Scalability | Time to scale out under load | Manual (hours) | < 2 minutes automated | HPA scale-out event logs | Per event |
| Cost Efficiency | Infrastructure cost per transaction | $0.0042 | < $0.0025 | AWS Cost Explorer / transaction volume | Monthly |
| Cost Efficiency | Annual infrastructure cost | $2.1M/year | < $1.4M/year | AWS Cost Explorer monthly report | Monthly |
| Developer Productivity | Onboarding time (new engineer) | ~3 weeks | < 1 week | Squad lead survey + onboarding task completion | Per hire |
| Developer Productivity | Lead time for change | ~3 weeks | < 3 days | GitLab DORA metrics integration | Weekly |
| Security | Critical/High CVEs in production | Not measured | 0 Critical, < 5 High | Trivy + Snyk dashboards; weekly scan reports | Weekly |
| Data Integrity | Post-migration data reconciliation | N/A | 100% parity | Automated reconciliation job pass rate | Per migration phase |

Table 9.1 – Success Metrics and KPIs with Baseline and Target Values

# 10. Appendices

## Appendix A – Glossary of Terms

| Term / Acronym | Definition |
| --- | --- |
| ADR | Architecture Decision Record – a document capturing an important architectural decision, its context, and consequences. |
| API Gateway | A server-side component that acts as the single entry point for client requests, handling routing, authentication, rate limiting, and transformation. |
| Bounded Context | A DDD concept defining the explicit boundary within which a domain model applies. Each microservice corresponds to one bounded context. |
| BFF | Backend for Frontend – a dedicated backend service tailored to the needs of a specific frontend client (web, mobile). |
| CDC | Change Data Capture – a technique for tracking row-level changes in a source database and propagating them to downstream systems. |
| Circuit Breaker | A resilience pattern that prevents cascading failures by stopping requests to a failing downstream service and returning a fallback response. |
| CQRS | Command Query Responsibility Segregation – separates read and write models to allow independent scaling and optimisation. |
| DDD | Domain-Driven Design – a software development approach focusing on modelling the business domain as the primary driver of technical design. |
| DMS | AWS Database Migration Service – a managed service for migrating databases to AWS with minimal downtime. |
| DORA Metrics | DevOps Research and Assessment metrics: Deployment Frequency, Lead Time for Changes, Change Failure Rate, and MTTR. |
| EKS | Amazon Elastic Kubernetes Service – a managed Kubernetes service on AWS. |
| Event Sourcing | A data pattern where state changes are stored as an immutable sequence of events rather than the current state alone. |
| GitOps | An operational model where the desired state of infrastructure and applications is declared in Git and automatically reconciled by tooling (e.g., ArgoCD). |
| gRPC | Google Remote Procedure Call – a high-performance RPC framework using Protocol Buffers for serialisation over HTTP/2. |
| HPA | Horizontal Pod Autoscaler – a Kubernetes resource that automatically scales the number of pods based on CPU, memory, or custom metrics. |
| IdP | Identity Provider – a system that creates, maintains, and manages identity information and provides authentication services. |
| Istio | An open-source service mesh providing traffic management, security (mTLS), and observability for microservices on Kubernetes. |
| JWT | JSON Web Token – a compact, URL-safe token format used for securely transmitting claims between parties as a JSON object signed with a private key. |
| Kafka | Apache Kafka – a distributed event streaming platform used for high-throughput, fault-tolerant asynchronous messaging. |
| KEDA | Kubernetes Event-Driven Autoscaling – extends HPA to scale based on external event sources such as Kafka consumer lag. |
| KMS | AWS Key Management Service – a managed service for creating and controlling cryptographic keys used to encrypt data. |
| mTLS | Mutual TLS – a variant of TLS where both the client and server authenticate each other using certificates. |
| MSK | Amazon Managed Streaming for Apache Kafka – a fully managed Kafka service on AWS. |
| MTBF | Mean Time Between Failures – the average time elapsed between recoverable failures of a system. |
| MTTR | Mean Time to Recovery – the average time taken to restore a system to full operation after a failure. |
| MTD | Mean Time to Deploy – the average duration from code commit to production deployment. |
| OpenTelemetry | An observability framework providing APIs and SDKs to instrument, generate, collect, and export telemetry data (metrics, logs, traces). |
| PII | Personally Identifiable Information – any data that could identify a specific individual, subject to GDPR and other data protection regulations. |
| Saga Pattern | A pattern for managing distributed transactions across multiple services using a sequence of local transactions, each publishing events to trigger the next step or a compensating transaction on failure. |
| SCT | AWS Schema Conversion Tool – converts source database schemas and application code to a target database engine. |
| SLO | Service Level Objective – a target value for a service level indicator (e.g., 99.9% availability over a rolling 30-day window). |
| SPIFFE | Secure Production Identity Framework for Everyone – a standard for workload identity in distributed systems. |
| Strangler Fig | A migration pattern where new functionality is incrementally built around the edges of the legacy system, eventually replacing it entirely. |
| Vault | HashiCorp Vault – a tool for secrets management, encryption as a service, and privileged access management. |
| Zero-Trust | A security model that assumes no implicit trust is granted to any entity inside or outside the network perimeter; all access must be explicitly verified. |

Table A.1 – Glossary of Terms and Acronyms

## Appendix B – References

| Ref # | Reference |
| --- | --- |
| 1 | Newman, S. (2021). Building Microservices: Designing Fine-Grained Systems (2nd ed.). O'Reilly Media. |
| 2 | Richardson, C. (2018). Microservices Patterns: With examples in Java. Manning Publications. |
| 3 | Evans, E. (2003). Domain-Driven Design: Tackling Complexity in the Heart of Software. Addison-Wesley. |
| 4 | AWS Documentation. Amazon EKS Best Practices Guide. https://aws.github.io/aws-eks-best-practices/ |
| 5 | AWS Documentation. AWS Database Migration Service User Guide. https://docs.aws.amazon.com/dms/ |
| 6 | CNCF. (2023). Cloud Native Trail Map. Cloud Native Computing Foundation. https://www.cncf.io/ |
| 7 | Google. (2023). DORA State of DevOps Report 2023. https://dora.dev/research/2023/ |
| 8 | Istio Documentation. Istio Service Mesh Architecture. https://istio.io/latest/docs/ |
| 9 | Confluent. Apache Kafka Documentation 3.7. https://kafka.apache.org/documentation/ |
| 10 | HashiCorp. Vault Architecture Overview. https://developer.hashicorp.com/vault/docs/internals/architecture |
| 11 | OpenTelemetry. OpenTelemetry Specification. https://opentelemetry.io/docs/specs/otel/ |
| 12 | PCI Security Standards Council. PCI DSS v4.0 (2022). https://www.pcisecuritystandards.org/ |
| 13 | ICO. Guide to the UK GDPR. https://ico.org.uk/for-organisations/uk-gdpr-guidance-and-resources/ |
| 14 | Fowler, M. Strangler Fig Application. https://martinfowler.com/bliki/StranglerFigApplication.html |
| 15 | Fowler, M. & Lewis, J. Microservices. https://martinfowler.com/articles/microservices.html |

Table B.1 – References and Further Reading

— End of Document —

Microservices Migration Technical Design Document  |  v1.0  |  July 2025  |  Internal – Confidential